## 2021 Calendar
LGITSA Information Security Calendar
ID | Task | Responsibility | Frequency | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01 | 2023-06-01
1 | Security Program Management
1.1 | Review Cyber Security Governance Framework |  | Annual | bar: 2022-07-01; 2022-09-01
1.2 | Review Information Asset Register |  | Annual | bar: 2022-09-01
1.3 | Review Security Risk Register |  | Annual | bar: 2022-09-01
1.4 | Review Statement of Applicability |  | Annual | bar: 2022-09-01
1.5 | Security Program Self Assessment |  | Annual | bar: 2022-10-01
1.6 | Security Program Independent Assessment |  | 2-years
1.7 | Review Measures and Metrics |  | Monthly | bar: 2022-02-01 to 2023-06-01
1.8 | Review Actions and Improvements Register |  | Monthly | bar: 2022-02-01 to 2023-06-01
1.9 | Security Working Group Meeting |  | Monthly | bar: 2022-02-01 to 2023-06-01
2 | Documentation
2.1 | Review of security policies | Policy Owners | Yearly | bar: 2022-06-01 to 2022-07-01; 2023-06-01
2.2 | Review of security procedures | Procedure Owners | Yearly | bar: 2022-04-01; 2022-07-01; 2023-04-01
2.3 | Review of operational procedures | Procedure Owners | Yearly | bar: 2022-03-01; 2022-07-01; 2023-03-01
3 | Personnel Security
3.1 | Conduct annual security training session(s) |  | Yearly | bar: 2022-08-01
3.2 | Validate that all security induction training has transpired |  | Monthly | bar: 2022-02-01 to 2023-06-01
3.3 | Issue quarterly phishing exercise |  | Quarterly | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01; 2023-02-01; 2023-05-01
3.4 | Validate personnel background checks are current | People & Culture / Human Resources | Quarterly | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01; 2023-02-01; 2023-05-01
4 | Supply Chain Security
4.1 | Review Supplier Security Assessment Register |  | Annual | bar: 2022-09-01; 2022-12-01
4.2 | Review Supplier Agreements | Procurement / Contract Owners | As required | bar: 2022-12-01
5 | Identity & Access Management
5.1 | Review Access Provisioning Processes for Critical Systems |  | Annual | bar: 2022-10-01
5.2 | Review Authentication Requirements for Critical Systems |  | Annual | bar: 2022-10-01
5.3 | Review Active Directory privileged access |  | Quarterly | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01; 2023-02-01; 2023-05-01
5.5 | Review Inactive Accounts |  | Monthly | bar: 2022-02-01 to 2023-06-01
5.6 | Review Active Directory Accounts |  | Annual | bar: 2022-11-01
5.7 | Password Compliance Review |  | Annual | bar: 2022-11-01
6 | Business Continuity & Incident Management
6.1 | Review Business Impact Assessments |  | Annual | bar: 2022-08-01
6.2 | Review Business Continuity Plan(s) |  | Annual | bar: 2022-08-01
6.3 | Review Disaster Recovery Plan(s) and System Recovery Plan(s) |  | Annual | bar: 2022-09-01
6.4 | Review Information Security Incident Response Processes |  | Annual | bar: 2022-09-01
6.5 | Test Business Continuity Plan(s) and validate RPO/RTO capabilities |  | Annual | bar: 2022-10-01
6.6 | Test Information Secuirity Incident Response Framework |  | Annual | bar: 2022-10-01
7 | Patching & Vulnerability Management
7.1 | Review Vulnerability Scanning Coverage - Internal |  | Annual | bar: 2022-10-01
7.2 | Review Vulnerability Scanning Coverage - External |  | Quarterly | bar: 2022-04-01; 2022-07-01; 2022-10-01; 2023-01-01; 2023-04-01
8 | End-Point Protection, Logging & Monitoring
8.1 | Perform Independent Penetration Testing |  | Annual | bar: 2022-12-01
9 | Asset, Change and Configuration Management
9.2 | Review System Configuration Baselines |  | Annual | bar: 2023-01-01
9.3 | Review Change Management Processes |  | Annual | bar: 2023-01-01
10 | Physical Security
10.1 | (SUBURB) Office Physical Security Review | Facilities Manager | Quarterly | bar: 2022-02-01; 2022-05-01; 2022-08-01; 2022-11-01; 2023-02-01; 2023-05-01
LEGEND
As required
Completed (C)
Work in Progress (W)
Overdue (O)
Deferred (D)
Planned (P)

## Cell Validation
Status
C
W
O
D
P